## Pre
PRE - CONFERENCE
START
TASK | CONTACT
Determine, apply and obtain sponsorship from all applicable IEEE and/or non-IEEE organizational units | Contact EPS Executive Office
12-9 Months
TASK | CONTACT
Register your conference with IEEE | IEEE Conference Application
Submit MOU/FaMOU (if applicable) | Click for more information on MoU/FaMoU
Submit IEEE Conference Publication Form - if applicable | IEEE Conference Publication Form
9-6 Months
TASK | CONTACT
Begin outreach to educational institutions, corporations, government and industry support and patronage
Develop technical program, establish paper submission process and deadlines. | Developing a Technical Program
Submission process should include CrossCheck | CrossCheck
Set-up online paper management system
6 Months
Promote Call for Papers
Review and reconfirm hotel meeting space and room block
Set registration fees
6-4 Months
Launch online registration
Complete paper review process. Finalize technical program. Notify authors.
Create and publish advance program
IEEE Electronics Packaging Society
Conference Timeline for Technically Sponsored Conferences

## Post
POST - CONFERENCE
1 Month Post
TASK | CONTACT
Submit Conference Proceedings/Content (Xplore CD and other media types) per LoA | Contact IEEE Conference Services
IEEE Electronics Packaging Society
Conference Timeline for Technically Sponsored Conferences